## 📊 Dashboard
VISTA WEBSITE OPTIMIZATION ¦ PROJECT DASHBOARD
AmeriCorps VISTA Program · Siena University · Academic Community Engagement
| 34 | 14 | 14 | +15% | 7 | 4
| Issues Identified | Issues Completed | In Progress | Avg SEO Lift | Pages Audited | Programs Covered
| 📈 SEO Score Improvements |  |  |  |  | 📋 Issues by Category
| Page | Before | After | Change | Status | Category | Total | Done | Rate
| AmeriCorps VISTA | 50% | 65% | +15% | ✅ | Content | 17 | 7 | 41%
| About Our Program | 38% | 56% | +18% | ✅ | Accessibility | 10 | 4 | 40%
| Open Positions | 56% | 66% | +10% | ✅ | Readability | 5 | 3 | 60%
| Meet the Team | 50% | 60% | +10% | ✅ | Other | 6 | 0 | 0%
| Our Stories | 35% | 45% | +10% | ✅
🏆 Key Wins & Project Highlights
| 🔑 | Access Expanded | Project performance led to expanded CMS permissions across the full Academic Community Engagement section
| ✅ | Critical Fix | Corrected Education Award amount (IL-4) — an ADA-compliance and legal accuracy issue
| 📝 | Content Rewrites | Plain-language rewrites improved readability scores; e.g. About Our Program: 29% → post-edit gain
| 🔍 | SEO Across 5 Pages | Added meta descriptions site-wide; average SEO score lifted from ~46% to ~58%
| ♿ | Accessibility Audit | Identified 38 images missing alt text and flagged heading structure issues across 7 pages
| 🔧 | Social Media Fix | Corrected incorrect icon swap: LinkedIn logo was displaying in place of Instagram
Scope: Front-end CMS editing only (Content & SEO tabs in BigTree) — no backend or code access ¦ Tools: WAVE · Screaming Frog SEO Spider · BigTree CMS · Manual Review

## VISTA Issue Tracker
Subpage Name | URL | Issue Description | Category | Tool Identified | Impact Level | Control Level | Risk Level | Status | Milestone | Notes | Column 1
AmeriCorps VISTA | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/ | [6 empty] | Not started
|  | 3 Linked Images Missing Alt texts | Accessibility | WAVE | IL-1 | CL-1, CL-3 | Low | In progress
|  | Fix heading skip structures (H1,H2,H3,H4) | Accessibility | WAVE | IL-1 | CL-1, CL-3 | Low | In progress
|  | 2 Contrast Errors (Low Contrast Text) | Accessibility | WAVE | IL-1 | CL-1, CL-3 | Low | In progress
|  | Change Page Header & Introduction | Content | Manual Review | IL-1 | CL-1, CL-3 | Low | Completed |  | Fight poverty and make a tangible difference.-> One year. Real impact. Lasting change.
|  | Delete Spin Section | Content | Manual Review | IL-3 | CL-1, CL-3 | Medium | Completed |  | Deleted Spin Section as it is no longer funded through AmeriCorps
|  | Refix the connect with us section (Social Media) for Facebook, Instagram, and Youtube | Content | Manual Review | IL-1, IL-2 | CL-1, CL-3 | Medium |  |  | LinkedIn Logo was swapped for the Instagram logo
|  | Add "We are Hiring Section" - change to link to the Open Positions URL page and add more content for Readability | Content | Manual Review | IL-1 | CL-1, CL-3 | Low |  |  | We are Hiring Section has been placed on the homepage
|  | Add Meta Descriptions | Accessibility | BigTree | IL-3 | CL-1, CL-3 | High |  |  | SEO: 50& -> 65% | 2026-04-08
|  | Add Callout Cards on each page | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
About Our Program | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/about-our-program/ | [6 empty] | Completed
|  | Education Award Amount | Content | Manual Review | IL-4 | CL-1, CL-3 | High | Completed
|  | Readibility Score Low (30%) - Edit Content in Paragraphs | Readibility | BigTree | IL-2 | CL-1, CL-3 | Medium | Completed | verified source: americorps.gov | SEO: 38& -> 56% Readibility Score is: 29%. Improved Readibility by decreasing sentences, using fewer syalbuls, and changing outdated information that causes confusion
|  | Delete Partners & Events and Outings | Readibility | Manual Review | IL-1 | CL-1, CL-3 | Low | Completed
|  | Language Modification | Readibility | Manual Review | IL-2, IL-1 | CL-1, CL-3 | Low, Medium | Completed |  | We are a diverse group that works together to fight poverty by building nonprofit capacity -> We’re a collaborative team committed to equipping nonprofits with the tools, strategy, and support they need to uplift communities.
|  | Add Meta Description | Accessibility | BigTree | IL-3 | CL-1, CL-3 | High | Completed |  |  | 2026-04-14
|  | Add Callout Cards on each page | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
Hide this section
Open Positions | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/open-positions/
|  | No Current Open Positions Posted - | Readibility | Manual Review | IL-3 | CL-1, CL-3 | Medium | Completed
|  | Upload Each Site Logo and resize to 740x740px | Content | Manual Review | IL-2 | CL-1, CL-3 | Low | Completed
|  | Upload each 26-27 VAD to BigTree CMS file storage | Content | Manual Review | IL-2 | CL-1, CL-3 | Low | Completed
|  | Add 21 Topic Rows: Photo - Site Logo , URL1: VAD, URL2: Site Website, Text: 1 sentence summarizing your position | Content | Manual Review | IL-2 | CL-1, CL-3 | Low | In progress
|  | Content: Apply Now - Link AmeriCorps Portal | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
|  | Add Meta Descriptions | Accessibility | [6 empty] | SEO: 56% -> 66% | 2026-04-14
|  | Content: Position Description - Link Position Descriptions | Content
Upload 15 VAD's to file respository
Add Literacy Volunteers
Delete VISTA Leader PD (2)
Meet the Team | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/meet-the-team/
|  | Erin Spence Contact Number | Content | Manual Review | IL-1 | CL-1, CL-3 | Low | Completed
|  | Erin Spence & Mya Zylberberg headshot | Content | Manual Review | IL-1 | CL-1, CL-3 | Low | Completed
|  | Add Meta Descriptions | Accessibility | BigTree | IL-3 | CL-1, CL-3 | High | In progress
|  | Add Callout Cards on each page | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
Add Bio's in callout cards
|  | Add Meta Descriptions | [7 empty] | SEO: 50% -> 60%
VISTA Calendar | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/vista-calendar/
|  | Meta Descriptions | Accessibility | BigTree | IL-3 | CL-1, CL-3 | High | In progress
|  | Add Callout Cards on each page | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
Information Sessions | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/info-sessions/
|  | Add New Information Sessions Dates Times, and Links | Content | Manual Review | IL-2 | CL-1, CL-3 | Medium | In progress
|  | Add Meta Description | Accessibility | BigTree | IL-3 | CL-1, CL-3 | High | In progress
Our Stories | https://www.siena.edu/centers-institutes/ace/ace-programs/americorps-vista-fellows/testimonials/
|  | Add New Stories | Readibility
|  | Add Meta Descriptions | Accessibility | BigTree | IL-3 | CL-3, CL-1 | High | In progress |  | SEO: 35% -> 45% | 2026-04-14
Benefits
Create a Benefits page
Add Benefits in Paragraph Section
VISTA PD Website Descriptions 2 - VISTA Position Descriptions

## Bonner Issue Tracker
Subpage | URL | Issue Description | Category | Tool Identified | Impact Level | Control Level | Risk Level | Status | MileStone | Notes
Bonner Service Leaders
|  | Add Meta Descriptions | [7 empty] | Join a legacy of impact. Bonner Service Leaders use academic talent to support nonprofits. Earn a Community Development Cert—Apply Now!
Carosuel of Photos or Grid
Prospective Bonners
|  | Add Meta Descriptions | [7 empty] | Discover the experience and benefits of being a Bonner. View our growth statistics and learn more about us to start your service journey.
Meet the Team
|  | Add Meta Descriptions | [7 empty] | Meet the Team behind our mission. Connect with our dedicated Bonner leadership team driving community change daily.
Card Section for Josh
Student Names and Class Year
PA's - seperate the section send list of roles
Stories
|  | Add Meta Descriptions | [7 empty] | Explore the impact of service through stories from our Bonner Service Leaders.
Hide Stories Page (Empty)
Optimize Meet the Team Section (Callout Card or table for students)
Partner Sites
New Section - New List

## NeXT Issue Tracker
Subpage | URL | Issue Description | Category | Tool Identified | Impact Level | Control Level | Risk Level | Status | MileStone | Notes
NexT Fellowship
|  | Add Meta Descriptions | [7 empty] | Join a legacy of excellence. Explore NeXT Fellowship requirements, see fellow publications, and discover why you should apply today.
Applications to express interest under Why I Should Apply? email aceinfo@siena.edu
Our Stories
|  | Add Meta Descriptions | [7 empty] | Hear from the source! Read authentic stories from past NeXT Fellows about their transformative experiences and professional growth.
Former Projects
|  | Add meta descriptions | [7 empty] | Review the impactful work of our fellows. Explore the past partnerships and diverse projects that define the NeXT Fellowship mission.
Add Logo's Topic Rows

## SPIn Issue Tracker
Subpage | URL | Issue Description | Category | Tool Identified | Impact Level | Control Level | Risk Level | Status | MileStone | Notes
Spin Homepage
|  | Meta | [7 empty] | Discover the Summer Project Incubator legacy. Explore interdisciplinary research projects, program benefits, and our latest project spotlights.
Update Dates and Homepage Numbers
Cleaning the Whitespace & Repetitive Language
Check from BaseCamp and pull there..
Repetitive Two Photos
Headings Change
Change URL routes for more accuracy
Previous Projects
|  | Meta | [7 empty] | See the impact of our work! Browse past partnerships and research projects completed by our fellows to solve community-wide challenges.
Testimonals
|  | Meta | [7 empty] | Read professional insights from past fellows. Learn how their experience with the Summer Project Incubator shaped their research careers.

## Copy of VISTA Issue Tracker
Subpage | URL | Issue Description | Category | Tool Identified | Impact Level | Control Level | Risk Level | Status | MileStone | Notes

## Legend
Impact Levels |  |  | Control Levels
Code | Name | Definition | Code | Name | Definiton
IL-4 | Critical | Legal Risk, ADA Exposure, severe accessibility barrier | CL-1 | Operational | I can directly fix
IL-3 | High | Significant UX, SEO, or performance impact | CL-2 | Configurational | Limited by CMS/theme
IL-2 | Moderate | Usability friction or strucutrsl improvement | CL-3 | Shared | Requires Collaboration
IL-1 | Low | Cosmetic or minor best practice issue | CL-4 | External | Vendor/platform controlled

## SEO - Issues Overview Audit
Issue Name | Issue Type | Issue Priority | URLs | % of Total | Description | How To Fix | Help URL
Page Titles: Below 30 Characters | Opportunity | Medium | 63 | 19.15 | Pages which have page titles under the configured limit. This isn't necessarily an issue, but it does indicate there might be room to target additional keywords or communicate your USPs. | Consider updating the page title to take advantage of the space left to include additional target keywords or USPs.
URL: Underscores | Opportunity | Low | 1 | 0.22 | URLs with underscores, which are not always seen as word separators by search engines. | Ideally hyphens should be used as word separators, rather than underscores. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
H1: Over 70 Characters | Opportunity | Low | 2 | 0.61 | Pages which have <h1>s over the configured length. There is no hard limit for characters in an <h1>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h1>s for users, including target keywords where natural for users - without keyword stuffing.
Links: Internal Outlinks With No Anchor Text | Opportunity | Low | 16 | 4.86 | Pages that have internal links without anchor text or images that are hyperlinked without alt text. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks without anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column is blank, or if an image, the 'Alt Text' column is also blank. Export in bulk via 'Bulk Export > Links > Internal Outlinks With No Anchor Text'. | Review the missing anchor text outlinks and where appropriate include useful and descriptive anchor text to help users and search engines.
Content: Readability Very Difficult | Opportunity | Low | 28 | 8.31 | Copy on the page is very difficult to read and best understood by university graduates according to the Flesch reading-ease score formula. Copy that has long sentences and uses complex words are generally harder to read and understand. | Consider improving the readability of copy for your target audience. Copy that uses shorter sentences with less complex words is often easier to read and understand.
Content: Exact Duplicates | Issue | High | 2 | 0.59 | Pages that are identical to each other using the MD5 algorithm which calculates a 'hash' value for each page and can be seen in the 'hash' column. This check is performed against the full HTML of the page. It will show all pages with matching hash values that are exactly the same. Exact duplicate pages can lead to the splitting of PageRank signals and unpredictability in ranking. | There should only be a single canonical version of a URL that exists and is linked to internally. Other versions should not be linked to, and they should be 301 redirected to the canonical version.
Meta Description: Over 155 Characters | Opportunity | Low | 49 | 14.89 | Pages which have meta descriptions over the configured limit. Characters over this limit might be truncated in Google's search results. | Write concise meta descriptions to ensure important words are not truncated in the search results, and not visible to users.
Security: HTTP URLs | Issue | High | 7 | 1.55 | HTTP URLs that are encountered in the crawl. All websites should be secure over HTTPS today on the web. Not only is it important for security, but it's now expected by users. Chrome and other browsers display a 'Not Secure' message against any URLs that are HTTP, or have mixed content issues (where they load insecure resources on them). To view how these URLs were discovered, view their 'inlinks' in the lower window tab. You can also export any pages that link to HTTP URLs via 'Bulk Export > Security > HTTP URLs Inlinks'. | All URLs should be to secure HTTPS pages. Pages should be served over HTTPS, any internal links should be updated to HTTPS versions and HTTP URLs should 301 redirect to HTTPS versions. HTTP URLs identified in this filter that are redirecting to HTTPS versions already should be updated to link to the correct HTTPS versions directly.
Meta Description: Missing | Opportunity | Low | 117 | 35.56 | Pages which have a missing meta description, the content is empty or has a whitespace. This is a missed opportunity to communicate the benefits of your product or service and influence click through rates for important URLs. | It's important to write unique and descriptive meta descriptions on key pages to communicate the purpose of the page to users, and entice them to click on your result over the competition. It can also mean Google use this description for snippets in the search results for some queries, rather than make up their own based upon the content of the page.
URL: Parameters | Warning | Low | 7 | 1.55 | URLs that include parameters such as '?' or '&'. This isn't an issue for Google or other search engines to crawl unless at significant scale, but it's recommended to limit the number of parameters in a URL which can be complicated for users, and can be a sign of low value-add URLs. | Where possible use a static URL structure without parameters for key indexable URLs. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
Meta Description: Duplicate | Opportunity | Low | 6 | 1.82 | Pages which have duplicate meta descriptions. It's really important to have distinct and unique meta descriptions that communicate the benefits and purpose of each page. If they are duplicate or irrelevant, then they will be ignored by search engines in their snippets. | Update duplicate meta descriptions as necessary, so important pages contain a unique and descriptive title for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
URL: Repetitive Path | Warning | Low | 1 | 0.22 | URLs that have repetitive paths or subfolders within the string (example.com/page1/page/page1/page2). In some cases this can be legitimate and logical, however it also often points to poor URL structure and potential improvements. It can also help identify issues with incorrect relative linking, causing infinite URLs. | While not always an issue repetitive paths aren't particularly user friendly, or could be causing crawling issues if due to incorrect relative linking. Ideally any URL should be as concise as possible. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
Images: Over 100 KB | Opportunity | Medium | 21 | 32.81 | Large images over a size threshold. Page speed is extremely important for users and SEO and often large resources such as images are one of the most common issues that slow down web pages. This filter simply acts as a general rule of thumb to help identify images that are fairly large in file size and may take longer to load. These should be considered for optimisation, alongside opportunities identified in the PageSpeed tab which uses the PSI API and Lighthouse to audit speed. This can help identify images that haven't been optimised in size, load offscreen, are unoptimised etc. | Uncompressed images bloat pages with unnecessary bytes, so ensure images are optimised with compression, properly scaled, and using the best image format to reduce file size where possible.
Links: Pages With High External Outlinks | Warning | Low | 60 | 18.24 | Pages that have a high number of followed external outlinks on them based upon the 'High External Outlinks' preferences under 'Config > Spider > Preferences'. External outlinks are hyperlinks to another subdomain or domain (depending on your configuration). This might be completely valid, such as linking to another part of the same root domain, or linking to other useful websites. External followed outlinks can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks' where the 'Follow' column is 'True'. | Review followed external outlinks to ensure they are to credible, trusted and relevant websites that are useful to your users.
H2: Non-Sequential | Warning | Low | 87 | 26.44 | Pages with an <h2> that is not the second heading level after the <h1> on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h2> is the second heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the heading element following an <h1> should be an <h2>, rather than an <h3>.
H2: Multiple | Warning | Low | 329 | 100 | Pages which have multiple <h2>s. This is not an issue as HTML standards allow multiple <h2>'s when used in a logical hierarchical heading structure. However, this filter can help you quickly scan to review if they are used appropriately. | Ensure <h2>s are used in a logical hierarchical heading structure, and update where appropriate utilising the full heading rank between (h3 - h6) for additional headings.
H2: Over 70 Characters | Opportunity | Low | 1 | 0.3 | Pages which have <h2>s over the configured limit. There is no hard limit for characters in an <h2>, however they should be clear and concise for users and long headings might be less helpful | Write concise <h2>s for users, including target keywords where natural for users - without keyword stuffing.
Page Titles: Over 561 Pixels | Opportunity | Medium | 23 | 6.99 | Pages which have page titles over Google's estimated pixel length limit for titles in search results. Google snippet length is actually based upon pixels limits, rather than a character length. The SEO Spider tries to match the latest pixel truncation points in the SERPs, but it is an approximation and Google adjusts them frequently. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
URL: Over 115 Characters | Opportunity | Low | 4 | 0.88 | URLs that are more than the configured length. This is generally not an issue, however research has shown that users prefer shorter, concise URL strings. | Where possible use logical and concise URLs for users and search engines. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
Response Codes: External No Response | Warning | Low | 4 | 0.8 | External URLs with no response returned from the server. Usually due to a malformed URL, connection timeout, connection error, or connection refused. View URLs that link to no responses using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > External > No Response inlinks'. | Malformed URLs should be updated to the correct location and other connection issues can often be resolved by using different user-agents ('Config > User-Agent'), adjusting the crawl speed ('Config > Speed') or disabling firewalls & proxies. If they can be viewed in a browser, then it's often not an issue.
Links: Non-Descriptive Anchor Text In Internal Outlinks | Opportunity | Low | 36 | 10.94 | Pages that have internal outlinks with anchor text that is not descriptive, such as 'click here' or 'learn more' based upon the preferences under 'Config > Spider > Preferences'. Anchor text is the visible text and words used in hyperlinks that provide users and search engines context about the content of the target page. Internal outlinks with non-descriptive anchor text can be seen in the 'Outlinks' tab, with the 'All Link Types' filter set to 'Hyperlinks', where the 'Anchor Text' column has words such as 'click here', or 'learn more'. Export in bulk via 'Bulk Export > Links > Non-Descriptive Anchor Text In Internal Outlinks'. | Review the non-descriptive anchor text in outlinks and where appropriate update them to include useful and descriptive anchor text to help provide context to both users and search engines.
Images: Missing Size Attributes | Opportunity | Low | 45 | 70.31 | Image elements without dimensions (width and height size attributes) specified in the HTML. This can cause large layout shifts as the page loads and be frustrating experience for users. It is one of the major reasons that contributes to a high Cumulative Layout Shift (CLS). | Define all image sizes as their native size using width and height attributes in the HTML. This allows the browser to calculate enough space for each image before it loads, avoiding large layout shifts.
H2: Duplicate | Opportunity | Low | 329 | 100 | Pages which have duplicate <h2>s. It's important to have distinct, unique and useful pages. If every page has the same <h2>, then it can make it more challenging for users and the search engines to understand one page from another. | Update duplicate <h2>s as necessary, so important pages contain a unique and descriptive <h2> for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
Page Titles: Over 60 Characters | Opportunity | Medium | 26 | 7.9 | Pages which have page titles that exceed the configured limit. Characters over this limit might be truncated in Google's search results and carry less weight in scoring. | Write concise page titles to ensure important words are not truncated in the search results, not visible to users and potentially weighted less in scoring.
URL: Internal Search | Warning | Low | 3 | 0.66 | URLs that might be part of the websites internal search function. Google and other search engines recommend blocking internal search pages from being crawled to limit sometimes duplicate and low quality pages from being crawled and indexed. | Most internal site searches are built for users, rather than search engines who may needlessly crawl and index them. As best practise most search sections of a site should not be linked to internally, and should be disallowed in robots.txt.
Canonicals: Missing | Warning | Medium | 337 | 100 | Pages that have no canonical URL present either as a link element, or via HTTP header. If a page doesn't indicate a canonical URL, Google will identify what they think is the best version or URL. This can lead to ranking unpredictability when there are multiple versions discovered, and hence generally all URLs should specify a canonical version | Specify a canonical URL for every page to avoid any potential ranking unpredictability if multiple versions of the same page are discovered on different URLs.
Meta Description: Below 400 Pixels | Opportunity | Low | 85 | 25.84 | Pages which have meta descriptions much shorter than Google's estimated pixel length limit. This isn't necessarily an issue, but it does indicate there might be room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
Images: Missing Alt Text | Issue | Low | 38 | 59.38 | Images that have an alt attribute, but are missing alt text. Click the address of the image and then the 'Image Details' tab in the lower window pane to view which pages have the image on them, and are missing alt text. Images should have descriptive alternative text about its purpose, which helps the blind and visually impaired, and the search engines understand it and its relevance to the web page. | Include descriptive alt text for images to help users and the search engines understand them better. Where possible, decorative images should be provided using CSS background images or alternatively a null (empty) alt text should be provided (alt="") so that they can be ignored by assistive technologies, such as screen readers.
H1: Non-Sequential | Warning | Low | 320 | 97.26 | Pages with an <h1> that is not the first heading on the page. Heading elements should be in a logical sequentially-descending order. The purpose of heading elements is to convey the structure of the page and they should be in logical order from <h1> to <h6>, which helps navigating the page and users that rely on assistive technologies. | Ensure the <h1> is the first heading on the page. Headings should be in a logical sequential order from <h1> to <h6>. Review and update page heading levels so they are descending in order, for example the first heading level should be an <h1>, and this should be followed by an <h2>.
Page Titles: Below 200 Pixels | Opportunity | Medium | 2 | 0.61 | Pages which have page titles much shorter than Google's estimated pixel length limit. This isn't necessarily an issue, but it does indicate there might be room to target additional keywords or communicate your USPs. | Consider updating the page title to take advantage of the space left to include additional target keywords or USPs.
Meta Description: Over 985 Pixels | Opportunity | Low | 45 | 13.68 | Pages which have meta descriptions over Google's estimated pixel length limit for snippets. Google snippet length is actually based upon pixels limits, rather than a character length. The SEO Spider tries to match the latest pixel truncation points in the SERPs, but it is an approximation and Google adjusts them frequently. | Write concise meta descriptions to ensure important words are not truncated in the search results, and not visible to users.
Page Titles: Duplicate | Opportunity | Medium | 15 | 4.56 | Pages which have duplicate page titles. It's really important to have distinct and unique page titles for every page. If every page has the same page title, then it can make it more challenging for users and the search engines to understand one page from another. | Update duplicate page titles as necessary, so each page contains a unique and descriptive title for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
Content: Readability Difficult | Opportunity | Low | 112 | 33.23 | Copy on the page is difficult to read and best understood by college graduates according to the Flesch reading-ease score formula. Copy that has long sentences and uses complex words are generally harder to read and understand. | Consider improving the readability of copy for your target audience. Copy that uses shorter sentences with less complex words is often easier to read and understand.
Response Codes: Internal Redirection (3xx) | Warning | Low | 47 | 9.4 | Internal URLs which redirect to another URL. These will include server-side redirects, such as 301 or 302 redirects (and more). View URLs that link to redirects using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Redirection (3xx) inlinks'. | Ideally all internal links would be to canonical resolving URLs, and avoid linking to URLs that redirect. This reduces latency of redirect hops for users, and enhanced efficiency for search engines.
H1: Duplicate | Opportunity | Low | 10 | 3.04 | Pages which have duplicate <h1>s. It's important to have distinct, unique and useful main headings. If every page has the same <h1>, then it can make it more challenging for users and the search engines to understand one page from another. | Update duplicate <h1>s as necessary, so important pages contain a unique and descriptive <h1> for users and search engines. If these are duplicate pages, then fix the duplicated pages by linking to a single version, and redirect or use canonicals where appropriate.
Security: Missing Content-Security-Policy Header | Warning | Low | 404 | 89.18 | URLs that are missing the Content-Security-Policy response header. This header allows a website to control which resources are loaded for a page. This policy can help guard against cross-site scripting (XSS) attacks that exploit the browser's trust of the content received from the server. The SEO Spider only checks for existence of the header, and does not interrogate the policies found within the header to determine whether they are well set-up for the website. This should be performed manually. | Set a strict Content-Security-Policy response header across all page to help mitigate cross site scripting (XSS) and data injection attacks.
Security: Missing X-Frame-Options Header | Warning | Low | 404 | 89.18 | URLs missing an X-Frame-Options response header with a 'DENY' or 'SAMEORIGIN' value. This instructs the browser not to render a page within a frame, iframe, embed or object. This helps avoid 'clickjacking' attacks, where your content is displayed on another web page that is controlled by an attacker. | To minimise security issues, the X-Frame-Options response header should be supplied with a 'DENY' or 'SAMEORIGIN' value.
Security: Unsafe Cross-Origin Links | Warning | Low | 40 | 8.83 | URLs that link to external websites using the target="_blank" attribute (to open in a new tab), without using rel="noopener" (or rel="noreferrer") at the same time. Using target="_blank" alone leaves those pages exposed to both security and performance issues for some legacy browsers, which are estimated to be below 5% of market share. Setting target="_blank" on <a> elements implicitly provides the same rel behavior as setting rel="noopener" which does not set window.opener for most modern browsers, such as Chrome, Safari, Firefox and Edge. The external links that contain the target="_blank" attribute by itself can be viewed in the 'outlinks' tab and 'target' column. They can be exported alongside the pages they are linked from via 'Bulk Export > Security > Unsafe Cross-Origin Links'. | Consider the benefits of including the rel="noopener" link attribute on any links that contain the target="_blank" attribute to avoid security and performance issues for the users of legacy browsers that may visit the website.
Security: Protocol-Relative Resource Links | Warning | Low | 25 | 5.52 | URLs that load resources such as images, JavaScript and CSS using protocol-relative links. A protocol-relative link is simply a link to a URL without specifying the scheme (for example, //screamingfrog.co.uk). It helps save developers time from having to specify the protocol and lets the browser determine it based upon the current connection to the resource. However, this technique is now an anti-pattern with HTTPS everywhere, and can expose some sites to 'man in the middle' compromises and performance issues | Update any resource links to be absolute links including the scheme (HTTPS) to avoid security and performance issues.
Meta Description: Below 70 Characters | Opportunity | Low | 93 | 28.27 | Pages which have meta descriptions below the configured limit. This isn't strictly an issue, but an opportunity. There is additional room to communicate benefits, USPs or call to actions. | Consider updating the meta description to take advantage of the space left to include additional benefits, USPs or call to actions to improve click through rates (CTR).
Content: Low Content Pages | Opportunity | Medium | 90 | 26.71 | Pages with a word count that is below the default 200 words. The word count is based upon the content area settings used in the analysis which can be configured via 'Config > Content > Area'. There isn't a minimum word count for pages in reality, but the search engines do require descriptive text to understand the purpose of a page. This filter should only be used as a rough guide to help identify pages that might be improved by adding more descriptive content in the context of the website and page's purpose. Some websites, such as ecommerce, will naturally have lower word counts, which can be acceptable if a products details can be communicated efficiently. | Consider including additional descriptive content to help the user and search engines better understand the page.
Security: Missing Secure Referrer-Policy Header | Warning | Low | 404 | 89.18 | URLs missing 'no-referrer-when-downgrade', 'strict-origin-when-cross-origin', 'no-referrer' or 'strict-origin' policies in the Referrer-Policy header. When using HTTPS, it's important that the URLs do not leak in non-HTTPS requests. This can expose users to 'man in the middle' attacks, as anyone on the network can view them. | Consider setting a referrer policy of strict-origin-when-cross-origin. It retains much of the referrer's usefulness, while mitigating the risk of leaking data cross-origins.
URL: Uppercase | Warning | Low | 5 | 1.1 | URLs that have uppercase characters within them. URLs are case sensitive, so as best practice generally URLs should be lowercase, to avoid any potential mix ups and duplicate URLs. | Ideally lowercase characters should be used for URLs only. However, changing URLs is a big decision, and often it's not worth changing them for SEO purposes alone. If URLs are changed, then appropriate 301 redirects must be implemented.
Security: Missing X-Content-Type-Options Header | Warning | Low | 404 | 89.18 | URLs that are missing the 'X-Content-Type-Options' response header with a 'nosniff' value. In the absence of a MIME type, browsers may 'sniff' to guess the content type to interpret it correctly for users. However, this can be exploited by attackers who can try and load malicious code, such as JavaScript via an image they have compromised. | To minimise security issues, the X-Content-Type-Options response header should be supplied and set to 'nosniff'. This instructs browsers to rely only on the Content-Type header and block anything that does not match accurately. This also means the content-type set needs to be accurate.
H1: Missing | Issue | Medium | 9 | 2.74 | Pages which have a missing <h1>, the content is empty or has a whitespace. The <h1> should describe the main title and purpose of the page and are considered to be one of the stronger on-page ranking signals. | Ensure important pages have concise, descriptive and unique headings to help users, and enable search engines to score and rank the page for relevant search queries.
H1: Multiple | Warning | Medium | 13 | 3.95 | Pages which have multiple <h1>s. While this is not strictly an issue because HTML5 standards allow multiple <h1>s on a page, there are some problems with this modern approach in terms of usability. It's advised to use heading rank (h1-h6) to convey document structure. The classic HTML4 standard defines there should only be a single <h1> per page, and this is still generally recommended for users and SEO. | Consider updating the HTML to include a single <h1> on each page, and utilising the full heading rank between (h2 - h6) for additional headings.
Response Codes: Internal Client Error (4xx) | Issue | High | 2 | 0.4 | Internal URLs with a client-side error. This indicates a problem occurred with the URL request and can include responses such as 400 bad request, 403 Forbidden, 404 Page Not Found, 410 Removed, 429 Too Many Requests and more. A 404 'Page Not Found' is the most common, and often referred to as a broken link. View URLs that link to errors using the lower 'inlinks' tab and export them in bulk via 'Bulk Export > Response Codes > Internal > Client Error (4xx) inlinks'. | All links on a website should ideally resolve to 200 'OK' URLs. Errors such as a 404 or 410 should be updated to their correct locations, removed and redirected where appropriate. A 403 forbidden error occurs when a web server denies access to the SEO Spider's request and can often be resolved by switching the user-agent to Chrome via 'Config > User-Agent' and crawling again.

## Page Overview
Page Name | URL | # Issues Identified | # Issues Fixed | Status | Overall Risk Level | SEO Before | SEO After | Accessibility Before | Accessibility After | Notes
AmeriCorp VISTA
About our Program
Open Positions
Meet the Team
VISTA Calendar
Info Session
Our Stories